# Weird Tales Premiere Preparation and Schedule

# By November 1

- Confirm the featured hosts for the village welcome. Get name tags for them.

- Complete a draft of Toni’s script and get Toni’s feedback.

- Confirm music. Taps, Paiute music, playlist for the flower building, Phylis is already confirmed.

- Confirm sound equipment for the playlist at the flower building. Phylis has her own sound equipment for the Museum.

- Make sure Ted has his equipment figured out and if he needs help with set up.

- Make sure the pop corn machine is scheduled and confirm who will work it.

- Confirmed food and beverage coordinator in charge of food and beverage.

By November 6

All sponsor posters must be in.

Food and beverage:

- Confirm Who will assist with Dan’s root beer serving

- Confirm who will man the popcorn machine and how it will get there.

- Confirm who will be in charge of setting up the food at the flower building and the museum.

- Double Confirm food and beverage that sponsors committed to.

November 10 - 12

Flower building set up

- Clean the flower building and set up chairs.

- Have the coffee and food serving dishes, in place at the flower building.

- Hang sponsor posters.

- Ted set up projection and sound at the Flower Building.

- Test film playback, sound, microphones, playlist, and music transitions.

November 10-12

- All food and beverage must be delivered to frig at flower building or museum.

- Serving dishes and paper plates and cups to museum and flower building.

# Event day preparation

- noon to 4:30 pm  Arrange refreshment tables at the museum and flower building. Prepare both refreshment stations and coffee service. Place candy and serving supplies. Keep appropriate food and drinks chilled until service.

- noon  Receive and set up the popcorn machine and root beer keg.

- 4 to 5 pm  Phyllis sets up

- 5 to 5:30 pm  Featured hosts arrive at suggested times for final checks. Brief the hosts, check Toni’s microphone and script, and confirm Ted’s screening and Q&A cues.

- 5:30 to 5:50 pm  Finish coffee and snacks; prepare popcorn and beverages. Ready last-minute ticket sales at the museum. Complete a final walk-through of both buildings.